## Project schedule
| University of Utah Regulation Change Project Plan |  |  |  |  | Project start: | [7 empty] | 2026-05-06
[6 empty] | Display week: | [7 empty] | 1
[6 empty] | 2026-05-04 | [6 empty] | 2026-05-11 | [6 empty] | 2026-05-18 | [6 empty] | 2026-05-25 | [6 empty] | 2026-06-01 | [6 empty] | 2026-06-08 | [6 empty] | 2026-06-15 | [6 empty] | 2026-06-22 | [6 empty] | 2026-06-29 | [6 empty] | 2026-07-06 | [6 empty] | 2026-07-13 | [6 empty] | 2026-07-20 | [6 empty] | 2026-07-27 | [6 empty] | 2026-08-03 | [6 empty] | 2026-08-10 | [6 empty] | 2026-08-17 | [6 empty] | 2026-08-24 | [6 empty] | 2026-08-31 | [6 empty] | 2026-09-07 | [6 empty] | 2026-09-14 | [6 empty] | 2026-09-21 | [6 empty] | 2026-09-28 | [6 empty] | 2026-10-05 | [6 empty] | 2026-10-12 | [6 empty] | 2026-10-19
| TASK | Person Responsible | Status | START | END | time axis 2026-05-04 to 2026-10-25
 | time axis 2026-05-04 to 2026-10-25
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Notification and Preparation
Determine regulation change and conduct research
Fill out regulation change proposal form
Receive approval from VP to pursue regulation change (note VP may delegate this step)
Notify Regulations Office of proposed regulations
Develop stakeholder consultation plan*
Regulation Development and Drafting - Initial Drafting
Establish whether to use a drafting committee and make-up of "drafting committee"
Draft proposed regulations change
Regulations Office and other writing committee members review first draft
Incorporate feedback from Regulations Office and drafting committee
Determine how to communicate policy change and create materials describing policy change, such as memo, tables, etc.
Prepare Implementation/Communication Plan
Update Institutional Policy Committee on progress
Incorporate Institutional Policy Committee feedback
Regulation Development and Drafting - Stakeholder Review
Send draft and memo to subject expert stakeholders included in plan
Meet with individual stakeholders as necessary and incorporate feedback
Send draft to committee or council stakeholders as listed in stakeholder tracking sheet
Meet with committee or council stakeholders as necessary and incorporate feedback
Update policy change memo to document stakeholders consulted
Formal Approval Process
Receive final approval from VP (typically policy officer)
Have final discussion with Institutional Policy Committee if necessary
Submit policy to President and Cabinet for final information
Present policy to Academic Senate Executive Committee for inclusion on Academic Senate Agenda
Present policy to Academic Senate
Receive Board of Trustees Approval
Regulations Office prepare for publication and publishes changes
Publish changes
Review changes
Communicate change with university community*
Implemented revised policy*
* = can develop a project plan specific to this topic
Insert new rows ABOVE this one

## Status Options
Not Started
In Progress
Complete
On Hold