## Project schedule
| University of Utah Regulation Change Project Plan |  |  |  |  | Project start: | [7 empty] | 2026-08-05
[6 empty] | Display week: | [7 empty] | 1
[6 empty] | 2026-08-03 | [6 empty] | 2026-08-10 | [6 empty] | 2026-08-17 | [6 empty] | 2026-08-24 | [6 empty] | 2026-08-31 | [6 empty] | 2026-09-07 | [6 empty] | 2026-09-14 | [6 empty] | 2026-09-21 | [6 empty] | 2026-09-28 | [6 empty] | 2026-10-05 | [6 empty] | 2026-10-12 | [6 empty] | 2026-10-19 | [6 empty] | 2026-10-26 | [6 empty] | 2026-11-02 | [6 empty] | 2026-11-09 | [6 empty] | 2026-11-16 | [6 empty] | 2026-11-23 | [6 empty] | 2026-11-30 | [6 empty] | 2026-12-07 | [6 empty] | 2026-12-14 | [6 empty] | 2026-12-21 | [6 empty] | 2026-12-28 | [6 empty] | 2027-01-04 | [6 empty] | 2027-01-11 | [6 empty] | 2027-01-18
| TASK | Person Responsible | Status | START | END | time axis 2026-08-03 to 2027-01-24
 | time axis 2026-08-03 to 2027-01-24
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
1. Notification and Preparation
1.1 Determine regulation change and conduct research
1.2 Notify University Regulations Office of Proposed Change
1.3 Receive approval from leadership team to pursue regulation change.
2. Regulation Development and Drafting
| 2.1 Create folder and draft structure and enter new project in Collibra | Regulations Office
2.2 Establish who needs to be involved with drafting proposed change
2.3 Develop stakeholder consultation plan
2.4 Draft proposed regulations change
2.5 Provide Regulations Office and other core developers with draft
2.6 Incorporate feedback from Regulations Office and core developers
2.7 Start developing materials describing policy change, such as memo, tables, etc.
3. Stakeholder Review and Incorporation of Feedback
3.1 Send draft and memo to subject expert stakeholders included in stakeholder review plan
3.2 Meet with individual stakeholders as necessary and incorporate feedback
3.3 Send draft to committee or council stakeholders as listed in stakeholder tracking sheet
3.4 Meet with committee or council stakeholders as necessary and incorporate feedback
3.5 Update policy change memo to document stakeholders consulted
3.6 Share drafts and consult with Institutional Policy Committee (Note - you may consult with the IPC at any time)
4. Approval and Publication
4.1 Submit policy to VP for final approval
4.2 At discretion of VP, determine if the Cabinet or other senior leaders need to be made aware of the change
4.3 Present policy to Academic Senate Executive Committee for determination of Academic Significance
4.4 Present policy to Academic Senate
4.5 Receive Board of Trustees Approval
| 4.6 Prepare draft for publication in the Regulations Library | Regulations Office
| 4.7 Publish changes | Regulations Office
4.8 Review changes
4.9 Communicate change with University Community
4.10 Implement revised regulation
Insert new rows ABOVE this one

## Status Options
Not Started
In Progress
Complete
On Hold